## Fit Gap Instructions
Fit Gap Analysis Spreadsheet
Overview of the Fit Gap Analysis Spreadsheet
Business Need:
In every engagement, Fits and Gaps between the business solution and the Customer requirements need to be identified and documented. Business processes that can operate by using the configured but non-customized standard business management solution can be determined as a Fit. The Gaps are business processes that cannot run completely by using the business management solution. Gaps might require custom code development, integration development, or solutions from independent software vendors (ISVs) It might also be reasonable and accepted to recommend a change to the business process as another way of addressing the requirement in the standard business solution.
This Fit Gap Analysis Spreadsheet is used to document the analysis based on areas of the business process. In the spreadsheet, each entry will be confirmed as either a Fit or defined as a Gap. Fit Gap analysis can disclose the exact details of the missing functionality, and identify where the business management solution can be optimized for usability.
The detailed Fit Gap analysis should be conducted based on the priority that the Customer has identified for each business requirement.
Fit Gap Analysis Tasks
Review the Customer Requirements in the Business Solution
1. Confirm and document as a Fit any business processes that can be run by using the business management solution.
2. Standard Features and Configuration settings and setup option values should be documented.
3. Define the importance/priority which the Customer has identified for all the requirements.
Document Gaps Between the Customer Requirements and Business Solution
1. Document Gaps for those business processes that cannot run completely by using the business solution.
2. Capture the nature and details of the Gaps and use examples where needed.
Analyze Gaps and Identify Solutions or Workarounds
1. Investigate resolutions or workarounds
2. Decide on the appropriate resolution
3. Update business processes documentation if needed.
4. Discuss resolution options with the Customer.
Document Gaps, Resolutions and Workarounds
Understanding the Fit Gap Analysis Spreadsheet
Summary Tabs:
There are two summary tabs available to be used to Report on the results of the Fit Gap Analysis:
1. Summary Standard Solution—This tab is used to reflect the degree of Fit for the standard business management solution without identifying any ISV solutions. This is helpful if the user wants to include the ISV solution as part of a Fit (therefore not identifying requirements with a category of ISV solution), It is also helpful if the user wants to take multiple stages of analysis and first provide degree of Fit analysis for the standard business management solution, and then identify the degree of Fit considering ISV solutions.
2.2. Summary with ISV Solution—This tab is used to reflect the degree of Fit for the standard business management solution incorporating any ISV solutions. On this tab, the ISV solution is considered part of Gap, so requirements that are addressed with an ISV solution must be categorized as such. This tab can also be used as part of a "stage two" approach to Fit Gap Analysis with ISV solutions, as previously described in the Summary Standard Solution section. The user can determine, based on the engagement, whether one or both tabs should be used.
The Summary tabs pull information directly from the Detail tabs. Each column heading correlates to one of the Detail tabs. Comments have been inserted in each business process area to help users understand the definition of these predefined areas. These areas can be changed, but the user needs to rename the corresponding Detail tab, as well. Users who require business process areas that are not already predefined in this template can take advantage of the Generic Industry-Specific Business Area Rows.
The cells in each row provide the totals and percentages of each business process area by categories. The categories are Standard Feature, Configuration, Workflow, and Customisation (and on the Summary with ISV Solution worksheet, ISV Solution). The degree of Fit is based on the combination of totals from Standard Features, Configuration, and Workflow for those requirements identified as Proof of Concept (POC), or Phase 1. Customisation and ISV solutions are considered to be part of the Gap component of the summary calculation. The business area on the Summary tabs captures the quantity of Phase 2 requirements but they are not part of the degree of Fit calculation.
The Summary tabs provide a total of all estimated hours to "build" the solution (that is, configuration and customisation) below the summary table. In addition, a pie chart is displayed to provide a graphical representation of the Fit/Gap distribution.
* Important Note: The Summary Standard Solution tab must never be deleted because it contains fields that the Detail tabs reference. These fields include the Customer name (Sample Customer) and business solution product name (Select Product). If users do not want to use the Summary Standard Solution tab, they must still populate information into these fields and then hide the worksheet.
Detail Tabs:
Each business process area has a separate tab for capturing business requirements for Fit Gap analysis. The Customer name and product name will automatically populate from the Summary Standard Solution tab.
The columns are as follows:
B : This column is hidden and contains formulas that are used to populate data in the Summary Tabs. It is critical that the formula is maintained and consistent for each row. Important - If the user wants to insert a row, it is essential that the formula is also copied into that row from column B.
C - #: This column contains the Requirement ID and should match the ID in the Functional Requirements Document (FRD), if applicable. It is recommended that this ID contain unique characters by business process area (for example, Financial Management = FM#) D - Description: The description of the Requirement – should match the FRD (if applicable). E - Importance: Use this column to prioritize Customer requirements. F - Category: View the categorization for the Summary tabs for Standard Feature, Configuration, Workflow, Customisation or ISV Solution. Please note that the "Other" category should be used in cases where there is no Gap alternative. G - Std Feature Comment: If the requirement is categorized as a Standard Feature, the user should capture how the requirement is met by the standard feature. H - Product Design Point: If the requirement is categorized as Configuration, the user should then capture how the requirement will be conceptually designed to meet that requirement.
I - Originated By: This column identifies where the requirement was initially communicated (for example, Request for Proposal (RFP), Customer Requirements documentation, requirements workshops etc.) J - Roll-out Phase: The user identifies the Phase classification for the requirement. POC indicates that the requirement will be part of a Diagnostic phase Proof of Concept and should be considered part of the Degree of Fit calculation. Phase 1 indicates that the requirement will be part of the initial roll-out and should be considered part of the Degree of Fit calculation. Phase 2 indicates that the requirement will be part of a future phase and should not be considered part of the Degree of Fit calculation. K - Hours: Capture estimated hours to configure, build, develop, and unit test the solution to meet the requirement. L: This column is hidden. Starting at row 71, the column contains the validation data for categorizing business requirements. Important: the user must be aware of what is contained in this column if they want to insert or delete rows.
Using the Fit Gap Analysis Spreadsheet
Instructions:
Populate the Fit Gap Analysis Spreadsheet based on requirements provided by the Customer by documentation or workshops. During the Analysis phase, the FRD is entered in the Fit Gap Analysis spreadsheet.
Major Steps to use the Tool
Step 1:
On the Summary Standard Solution tab, enter Customer name in the SAMPLE CUSTOMER list.
On the Summary Standard Solution tab, select the Business Solution Product name in the [ SELECT PRODUCT] Design Point list.
Step 2:
Decide if you will be using one or both of the Summary tabs (see previous details for further use and definition of each).
Hide the summary tab that is not being used (if applicable).
Step 3:
Ensure that the tabs represent the business process areas of your Customer. If you want to rename a business process area, first rename the Detail tab, which will update all associated formulas. After you have renamed the Detail tab, you can rename the row in the Summary tabs. It is highly recommended that you do not delete any tabs in this sheet. If tabs are not being used, users are encouraged to simply hide them to avoid damaging formulas and references that the sheet requires to properly report information. It is also much easier to rename and use tabs that were not previously being used than to create new ones. As previously noted in the Detail tabs section, Generic Industry-Specific Business Area rows have been included for users who require business process areas that are not already predefined in the template. If they still require an additional tab, they should create a duplicate copy of an existing tab and rename it. The user will then have to insert a row on the Summary tab, and enter the appropriate formulas to ensure that information is properly represented.
Step 4:
Document Business Requirements and complete Fit Gap Analysis by entering data into the columns on the Detail tabs.
Step 5:
Verify that the Summary tabs and all requirements and totals are reflected and represented correctly.

## Summary
Degree of Fit Analysis |  |  |  | Sample Customer |  |  | Microsoft Dynamics CRM
Area | Total # of Individual Requirements | Phase 1 | [10 empty] | Phase 2 | Add-In Required | Comments
|  | Std Features |  | Configuration |  |  | Workflow |  |  | Customisation
|  | # | % | # | % | Hours | # | % | Hours | # | % | Hours
Accounts | 5 | 2 | 40% | 1 | 20% | 16 | 1 | 20% | 8 | 1 | 20% | 8 | 0
Contacts | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0
Activities | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0
Leads | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0
Opportunities | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0
Campaigns | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0
Other | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0
Total | 5 | 2 | 40% | 1 | 20% | 16 | 1 | 20% | 8 | 1 | 20% | 8 | 0
|  |  | Degree of Fit*: | 80%
*N.B. This analysis only considers those requirements deemed to be in Phase 1 which includes those requirements to be demonstrated in the Conference Room Pilot (CRP).
Requirements deemed Phase 2 as they were "Nice to Have" were not included in this analysis.
[12 empty] | Total Configuration and Development Man Days (Phase 1) = | 4
Note on L11: SDK standard for Software Development Kit. This a development environment provided by CRM based on .Net, Visual Studio and Web Services.

## Accounts
Microsoft CRM Implementation
|  | Business Object/Area: Accounts |  | Solution Map and Fit Gap
Customer: Client X
Business Requirements
| # | Description | Importance | Category | Standard Feature Comments | CRM Design Point | Originated by | Rollout Phase | Estimated Hrs.
The following are best practice considerations when performing a fit gap for this business area. Each comes with an example answer:
ConfigurationPhase 1 | 1 | Provide information on customer profile | Medium | Configuration | New attributes to capture customer profile data |  | Req Doc | Phase 1 | 16
Std FeaturePhase 1 | 2 | Ability to share account records with other users | High | Std Feature |  |  | Req Doc | Phase 1
CustomisationPhase 1 | 3 | Retrieval of Account information from SAP | Medium | Customisation |  |  | Req Doc | Phase 1 | 8
WorkflowPhase 1 | 4 | Automatic generation of activities when an account is created | High | Workflow |  |  | Req Doc | Phase 1 | 8
Std FeaturePhase 1 | 5 | Sorting account records via column titles | Medium | Std Feature |  |  | Req Doc | Phase 1
| 6 | <<Add Business Requirement as Needed but copy same format including hidden cells!!!>>
Form Modifications: (views, tabs, sections, fields)
| # | Action (add chg delete) | Field Name | Tab | Section | CRM Field Name | Type | Length | Comments

## Contacts
Microsoft CRM Implementation
| Business Object/Area: Contacts |  | Solution Map and Fit Gap
Customer: Client X
Business Requirements
# | Description | Importance | Category | Standard Feature Comments | CRM Design Point | Originated by | Rollout Phase | Estimated Hrs.
The following are best practice considerations when performing a fit gap for this business area. Each comes with an example answer:
| Ability to specify which business units can view a contact record or make it globally available. |  |  | Handled via standard permissions with business units and roles.
| Ability to control read, write, create and delete on contact records. |  |  | Handled via standard permissions with business units and roles.
| Client Annotations - notes, events, actions, attaching documents (different types) |  |  | Notes, activities and attachments maybe linked to client records
| Ability to view open and historical activities (emails, phone calls, appointments, tasks etc.) |  |  | Activities already have this relationship to the system Contact record.
| Ability to create mailings and communication lists based on contact information. |  |  | The Advanced Find feature in CRM can be used to query any information in the contact record or related entity records. This information can be used for direct emails. Also, using the query capabilities, communication lists can be managed.
<<Add Business Requirement as Needed but copy same format including hidden cells!!!>>
Form Modifications: (views, tabs, sections, fields)
# | Action (add chg delete) | Field Name | Tab | Section | CRM Field Name | Type | Length | Comments

## Activities
Microsoft CRM Implementation
| Business Object/Area: Activities |  | Solution Map and Fit Gap
Customer: Client X
Business Requirements
# | Description | Importance | Category | Standard Feature Comments | CRM Design Point | Originated by | Rollout Phase | Estimated Hrs.
The following are best practice considerations when performing a fit gap for this business area. Each comes with an example answer:
Instant view of activities pertaining to a business from the business form
View related service requests from business form.
Track emails sent using Outlook in CRM
| Ability for any person to create notes/comments for customers and complaints |  |  | Notes are accessible to users that have access to the entity form.
| Grouping of active and inactive cases in separate views |  |  | System views for Active and Inactive Cases
<<Add Business Requirement as Needed but copy same format including hidden cells!!!>>
Form Modifications: (views, tabs, sections, fields)
# | Action (add chg delete) | Field Name | Tab | Section | CRM Field Name | Type | Length | Comments

## Leads
Microsoft CRM Implementation
| Business Object/Area: Leads |  | Solution Map and Fit Gap
Customer: Client X
Business Requirements
# | Description | Importance | Category | Standard Feature Comments | CRM Design Point | Originated by | Rollout Phase | Estimated Hrs.
The following are best practice considerations when performing a fit gap for this business area. Each comes with an example answer:
Manual or import of leads typically from an Excel file
Ability to modify leads
Ability to convert an activity ( such as a phone call) into a lead
Ability to disqualify a lead
Ability to resurrect a lead
Turning a lead into an opportunity
<<Add Business Requirement as Needed but copy same format including hidden cells!!!>>
Form Modifications: (views, tabs, sections, fields)
# | Action (add chg delete) | Field Name | Tab | Section | CRM Field Name | Type | Length | Comments

## Opportunities
Microsoft CRM Implementation
| Business Object/Area: Opportunities |  | Solution Map and Fit Gap
Customer: Client X
Business Requirements
# | Description | Importance | Category | Standard Feature Comments | CRM Design Point | Originated by | Rollout Phase | Estimated Hrs.
The following are best practice considerations when performing a fit gap for this business area. Each comes with an example answer:
Ability to assign and share opportunities
Ability to relate opportunities to activities or other records
Use of workflow to automate the sales process
e.g. typically a sales process has from 3 to 12 stages ranging from initial contact to closure
Ability to close. Reopen and delete opportunities
<<Add Business Requirement as Needed but copy same format including hidden cells!!!>>
Form Modifications: (views, tabs, sections, fields)
# | Action (add chg delete) | Field Name | Tab | Section | CRM Field Name | Type | Length | Comments

## Campaigns
Microsoft CRM Implementation
| Business Object/Area: Campaigns |  | Solution Map and Fit Gap
Customer: Client X
Business Requirements
# | Description | Importance | Category | Standard Feature Comments | CRM Design Point | Originated by | Rollout Phase | Estimated Hrs.
The following are best practice considerations when performing a fit gap for this business area. Each comes with an example answer:
| Ability to compare like with like campaigns. |  |  | Campaign Comparison Reports is available to compare two campaigns.
| Ability to search for campaigns based on region and project. |  |  | Advanced Find
| Ability to export to excel. |  |  | Export to Excel is standard functionality
| Ability to select survey participants based on search criteria (e.g. all customers in the Eastlakes development who have settled in the last 2 weeks, all residential customers in QLD). |  |  | Advanced Find.
| Ability to auto-generate email and mail and track responses |  |  | Email templates can be setup, and emails sent can have responses tracked
<<Add Business Requirement as Needed but copy same format including hidden cells!!!>>
Form Modifications: (views, tabs, sections, fields)
# | Action (add chg delete) | Field Name | Tab | Section | CRM Field Name | Type | Length | Comments

## KB
Microsoft CRM Implementation
| Business Object/Area: Knowledge Base |  | Solution Map and Fit Gap
Customer: Client X
Business Requirements
# | Description | Importance | Category | Standard Feature Comments | CRM Design Point | Originated by | Rollout Phase | Estimated Hrs.
The following are best practice considerations when performing a fit gap for this business area. Each comes with an example answer:
| Ability to associate knowledge base articles with the same subjects cases/requests are related to and filter/search based on these subjects. |  |  | Knowledge Base articles are required to be associated with a subject. When in a case/request where a subject is selected, KB articles will be pre-filtered accordingly. A user can search based on subjects.
| Ability to enter comments regarding KB articles |  |  | Users can enter article comments in the comments area.
| Ability to have templates for creating KB articles to promote format consistency. |  |  | Knowledge Base articles can be created/generated off of Article templates.
| Ability to have hyperlink URL in Knowledge Base Article |  |  | URLs work as hyperlinks when published in an article.
<<Add Business Requirement as Needed but copy same format including hidden cells!!!>>
Form Modifications: (views, tabs, sections, fields)
# | Action (add chg delete) | Field Name | Tab | Section | CRM Field Name | Type | Length | Comments

## General
Microsoft CRM Implementation
|  | Business Object/Area: Other |  | Solution Map and Fit Gap
Customer: Client X
Business Requirements
| # | Description | Importance | Category | Standard Feature Comments | CRM Design Point | Originated by | Rollout Phase | Estimated Hrs.
The following are best practice considerations when performing a fit gap for this business area. Each comes with an example answer:
Std Feature |  | Ability to easily define contents of drop-down lists | Medium | Std Feature | Schema manager within settings. Can only be modified by system administrator
Std Feature |  | Web client functionality through standard Internet Explorer | High | Std Feature | CRM web client UI
Std Feature |  | Record ownership | High | Std Feature | By default each user owns the record which they created.
Std Feature |  | Ability to assign records to other users | High | Std Feature | Standard assign feature
Std Feature |  | Ability to share records with users and teams | Medium | Std Feature | Standard sharing of records between users and teams
|  | Ability to have hyperlink URL in Knowledge Base Article |  |  | URLs work as hyperlinks when published in an article.
<<Add Business Requirement as Needed but copy same format including hidden cells!!!>>
Form Modifications: (views, tabs, sections, fields)
| # | Action (add chg delete) | Field Name | Tab | Section | CRM Field Name | Type | Length | Comments