## Project Documents
WVOT Project Workbook (Work in Progress)
Project:
Project #:
Project Manager:
Project Sponsor:
Project Artifacts:
Updated:
Project Documents | [5 empty] | Required Documents and Processes
[6 empty] | Customer Preference | Regulatory | PM Oversight | Project | RFP
Initiating | Statement of Work
Business Case
Project Charter or Project Mini Charter
Concept Paper
Contact List
PC Stakeholder Register
Project Consolidation Checklist
Planning | Project Plan - Tasks, Resource, Schedule, include milestones and deliverables
Roles and Responsibilities: Finalize and Establish Project Management Team
Kick-Off Meeting Items
Project Governance Plan
Requirements Specification Document
Functional
Technical
Security
Regulatory
Other
Requirements Management Plan
Work Package Management Plan
Infrastructure Document
Cost Estimate and Budget Plan (Project Budget Sheet)
Communications Plan
Contractor Management Plan
Change Management with defined approval process (Change Log)
Issue Management (Issue Log)
Planning (cont) | Quality Management Plan
Define Key Performance Indicators
Other Project Metrics
Determine and Define External Reporting Processes
Risk Management (Initial risk will be identified in the SOW)
Training Plan
Deployment Plan (Initiation)
Lessons Learned (Initiation)
Identify and Acquire Project Tools
SELECT: Computer Accounts, OCS, VPN, SharePoint, Primavera, Outlook, Visio, Code Tracking, Version Control
Determine and Setup the technology environment. SELECT: sandbox, development, test, training, production and OTHER.
Testing Plan and Testing Acceptance
Data Conversion Plan
Executing | To be further defined after Planning Documents and Processes are Confirmed
Status Reporting (specific project status worksheet included in workbook)
Change Management with defined approval process (Change Log)
Issue Management (Issue Log)
Closing | Confirm Completion of Training and Documentation Plans
Procurement Audit
Deployment Plan
Cut over Activities
Maintenance and Support Plan
Lessons Learned
Project Closeout Checklist
Release / Reassign Staff (Select: accounts, computer tools, access cards, etc.)
Monitoring & Controlling | Budget Tracking (weekly - Status includes budget, schedule, scope, issues, accomplishments and action items)
Action Items Log
Status Report
Issue Log
Risk Tracking Log
Change Log
Lessons Learned
Project Phase Exit Plan
Deliverable Acceptance Log
Customer Check-In Log
Change Tracking for the Project Documents
Version | Type of Change: Add, Modify, Delete |  | Description of Change | Approved | Date | The Project Management Workbook is a Work In Process,
subject to Corrections and Additions.
Note on L10: b209057: need to indicate SOW or charter is needed for PM but not both

## Mini Project Charter (PC)
PROJECT MINICHARTER
Project : | 0
Project #: | 0
Project Manager: | 0
Project Sponsor: | 0
Project Artifacts:
Updated:
Project Definition
Project Justification
Objectives
Scope | In Scope | Out of Scope
Risks | Please see the Risk Tracking Log tab within the Project Workbook
Assumptions and Constraints | Assumptions & Constraints |  | Category
Stakeholder Register | Please see the PC - Stakeholder Register tab within the Project Workbook
Authority Level of PM
Signatures
Sponsor (Primary Stakeholder) | Signature:
Printed Name:
Date:
Project Manager | Signature:
Printed Name:
Date:
Note on B17: Note A for assumptions, C for constraints
Note on H17: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on I17: Withrow, Cathy A: Need to compare SOW and CHARTER.
Note on B25: Riley, Angela Y: Items to be considered Timesheets Overtime Leave Slips Assignment of tasks

## PC - Stakeholder Register
STAKEHOLDER REGISTER
Project : | 0
Project #: | 0
Project Manager: | 0
Project Sponsor: | 0
Project Artifacts:
Updated:
Name | Title | Organization | Office Location / Address | Work Hours | Office: Phone Number | Mobile: Phone Number | Email Address | Preferred Communication Method | Area of Interest | After Hours Contact Info | Time Zone | Secondary Contact | Manager Contact
Note on I8: Riley, Angela Y: Use the column to identify the contact's preference for communication - email; office phone, cell phone etc.
Note on L8: b673772: Enter time zone EST; CST; MST; PST

## Roles Responsibilities
Roles & Responsibilities
Project: | 0
Project #: | 0
Project Manager: | 0
Project Sponsor: | 0
Project Artifacts:
Updated:
| Project Manager | Individual Assigned | Start Date | End Date
| • Manages project in accordance with the EPMO methodology | 0
• Serves as liaison to Project Sponsor
• Provides overall project direction and leads team members toward project objectives
• Vehicle for project status
• Manages project budget
• Handles problem resolution
Customer Relationship Manager
• Provides project oversight and guidance
• Provides knowledge and understanding of the Office of Technology (OT), its mission, services and value to our customers
• Advocate to ensure that technology solutions align with Customer objectives, and that Customer requirements are met and prioritized within OT
• Knowledgeable of the Customer's political and business drivers
• Advocate to maintain a positive relationship between the Customer and OT
• Works with Customer to refine the Concept Paper and services questions
• Monitors and acts upon tasks that affect overall customer service
• Works with the Customer and Project Manager to address project issues
• Works with Customer, Project Manager and OT Director to provide standards and process improvements
Project Sponsor
| • Ultimate decision-maker and tie-breaker | 0
• Reviews/approves all project deliverables
Technical Lead
Agency Project Manager / Lead
• Understands the user needs and business processes in their area
• Acts as advocate in representing their area
• Communicates project goals, status and progress throughout the project to personnel in their area
• Reviews and approves project deliverables
• Creates or helps create work products, such as use cases
• Coordinates participation of work groups, individuals and stakeholders
• Provides knowledge and recommendations
• Helps identify and remove project barriers
• Assures quality of products that will meet the project goals and objectives through active participation in black-box-testing as part of User Acceptance Testing
• Identify risks and issues and help in resolutions

## Communication Plan
COMMUNICATION PLAN
Project: | 0
Project #: | 0
Project Manager: | 0
Project Sponsor: | 0
Project Artifacts:
Updated:
Item/Message | Frequency (When) | Delivery Channel (Email, phone, web) | Item/Message Owner (For approval) | Authorized Messenger | Sensitivity or Classification | Authorized Recipients/Attendees
Project Kickoff
Project Plan
Team Meetings Notes
Weekly Quick Updates
Project Status Reports
Budget
Entry in WVOT Project Dashboard
Major Milestone Announcements
Issues, Action Items and Lessons Learned
Project Close Out Report
Issues Work Assignments
Vendor Communications
Training
Public Type Announcement
Project Changes
INSTRUCTIONS
Italicized items are provided for example only. Modify content of the columns to meet project specific needs.
The Communications Plan outlines the roles and responsibilities of project participants in the review, approval and dissemination of information about key project processes, events, documents, news/announcements, quick guides, training materials, etc.
The Project Communications Plan will:
· Help manage expectations regarding the project.
· Assure appropriate levels of communication with internal and external project stakeholders.
· Provide relevant, accurate, consistent information at all times.
· Generate and sustain enthusiasm and support for the project.
The Project Communications Plan must be developed by the Planning Process stage of the project. The information to be collected and the basic steps to collect this information is as follows:
What – List items or occurrences to be communicated.
When and Frequency - Indicate when the item should be generated and or updates distributed.
How – Indicate the form the communication will take.
Owner – Indicate the name of the person or team responsible for producing and/or delivering the communication.
Approval - Indicate the name of the person or team responsible for approving release of certain communication
Classification - Classify the communications to distinguish between information that should be shared with the public, sponsors, and internal team members.
Recipients/Attendees – Indicate an appropriate level of involvement for that person, entity or group.
Note on A19: Usually functional and technical leads.

## Status Report
WVOT P3 Management Board Project Status Report
|  |  |  | Budget, Schedule, and Scope Status |  | Green (Controlled) | Yellow (Caution) | Red (Critical)
Status Report Date :
Project Type: |  |  |  | Budget | Original (Current Approved)
Department: |  |  |  |  | Actual Exp. to Date
Agency: |  |  |  | Schedule | Original
Project Sponsor: |  |  |  |  | Current Approved
Project Name: |  |  |  | Scope | Scope Changes:
Project Manager:
Start Date – End Date:
End State:
Location of Artifacts:
Attachments? (If yes, list):
| Issues | Status | Date Opened | Impact |  | Assigned to | Requested Due Date | Date Closed
1
2
3
4
| Risks | Trigger Event/Indicator | Risk Response |  |  | Probability | Impact | Owner
1
2
3
4
| Action Items |  |  |  | Status | Assigned to | Date Opened | Completion Date
1
2
3
Accomplishments
1
2
3

## Project ASR
Project Activity, Schedule, and Resources
Project: |  | 0 | 0
Project #: |  | 0 | 0
Project Manager: |  | 0 | 0
Project Sponsor: |  | 0 | 0
Project Artifacts:
Updated:
ID | Activity Name | Dependencies and Predecessors | Resource | Duration (days) | Start | Due Date (Finish) | Labor Cost | Equip. Cost | Other Costs

## Risk Tracking Log
RISK MANAGEMENT MATRIX (Risk Register)
| Project: | 0
| Project #: | 0
| Project Manager: | 0
| Project Sponsor: | 0
Project Artifacts:
ID | Updated: | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response | Response Description | Owner | Status | Date to Review | Entered By | Date Entered
| What is this risk? | [5 empty] | What act or event initiates either the risk occurrence or precipitates the response strategy? |  |  | Who monitors this risk?
1 |  |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
Note on C7: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on D7: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on E7: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on G7: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on I7: Options are: Avoidance Transference Mitigation Acceptance
Note on J7: Riley, Angela Y: A description of what actions are taken to implement the response. This is also referred as the contingency plan or mitigation plan
Note on K7: b209057: This is the person who is responsible for monitoring the risk not the person who is responsible for implementing the response plan
Note on L7: Options are: Open Closed
Note on M7: Riley, Angela Y: The date or frequency that someone is to monitor for the risk.
Note on N7: Riley, Angela Y: The person who entered the risk into the log.
Note on O7: Riley, Angela Y: The date the risk was entered into the log.

## Issue Log
Issues / Watch Items Log
| Project: | 0
| Project #: | 0
| Project Manager: | 0
| Project Sponsor: | 0
Project Artifacts:
Updated:
No. | WBS (optional) | Description | Status | Category | Impact | Priority | Assigned To | Resolution | Date Closed | Identified By | Date Entered | Notes
1
2
3
4
5
6
7
8
9
10
Note on D8: B271542: OPEN, CLOSED - Resolved, CLOSED - NOT Resloved, ONHOLD, Transferred
Note on E8: B271542: Business Process, Functional, Personnel, Technical,

## Action Items Log
ACTION ITEMS
| Project: | 0
| Project #: | 0
| Project Manager: | 0
| Project Sponsor: | 0
Project Artifacts:
Updated:
No. | WBS (optional) | Action Item Title/Description | Status | Priority | Assigned To | Planned Completion | Actual Completion | Date Entered | Entered By | Comments
1
2
3
4
5
6
7
8
9
10
Note on D8: B271542: Pending Assignment Active - Assigned On Hold Canceled Complete

## Change Log
CHANGE CONTROL LOG
Project: | 0
Project #: | 0
Project Manager: | 0
Project Sponsor: | 0
Project Artifacts:
ID | Change Description | Category | Priority | Requestor | Justification | Impact on Budget, Scope, Schedule, and / or Agreements (SLA, Contract, etc.) | Date Assigned | Assigned To | Status | Evaluator / Decision Maker | Date of Decision | Alternatives | Resolution | Notes | Date Entered | Entered By
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Change Tracking for the Change Log
Version | Type of Change: Add, Modify, Delete | Description of Change
Note on D7: B271542: Business Process, Financial (Budget), Functional, Personnel, Regulatory / Security, Technical, Other
Note on E7: Options are: 3: High 2: Medium 1: Low 0: NA
Note on F7: Who identified the change needed?
Note on K7: Options are: Under Review Rejected Approved On Hold
Note on L7: Riley, Angela Y: Who will decide what action is taken on the change?

## Project Budget Sheet
BUDGET
Project: | 0
Project #: | 0
Project Manager: | 0
Project Sponsor: | 0
Project Artifacts:
Updated:
Personnel | Rate | Acquired Hours | Original | Actual | Difference | Original | Actual | Difference | Original | Actual | Vendor Difference | Original | Actual | Difference | Reason for Change
WVOT Project Manager |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT Business Analyst |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT Developer |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT DBA |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT Infrastructure Expert |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT Network Engineer |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT Account Mgt |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT ??? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT Security |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT Q&A |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
WVOT CRM |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Vendor Project Manager |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Vendor Business Analyst |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Vendor Developer |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Vendor DBA |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Vendor Infrastructure Expert |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Vendor Network Engineer |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Operating | Rate | Quantity | Original | Actual |  | Original | Actual |  | Original | Actual |  | Original | Actual | Difference
Servers |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Operating System |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
Software Licenses |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Could be serveral licenses
Software Assurance |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Deliverable Acceptance Log
DELIVERABLE ACCEPTANCE LOG
Project: |  | 0 | 0
Project #: |  | 0 | 0
Project Manager: |  | 0 | 0
Project Sponsor: |  | 0 | 0
Project Artifacts:
Updated:
ID | Deliverable Description |  | Comments | Evaluator | Status | Date of Decision | Evaluator Initials
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Note on G8: Options are: In review Rejected Accepted

## Lessons Learned
LESSONS LEARNED
Project: | 0
Project #: | 0
Project Manager: | 0
Project Sponsor: | 0
Project Artifacts:
Updated:
Item | Date Entered | Process | DESCRIPTION
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Change Tracking for the Lessons Learned Log
Version | Type of Change: Add, Modify, Delete |  |  | Description of Change | Approved By | Date
What went well? What went wrong? What will we do next time?

## Customer Check-In Log
Customer Check-In Log
Project: |  | 0 | 0
Project #: |  | 0 | 0
Project Manager: |  | 0 | 0
Project Sponsor: |  | 0 | 0
Project Artifacts:
Updated:
Notes/Alerts:
DATE | PERSON CONTATCED | ATTEMPTED | TOPICS DISCUSSED | RESPONSE | ACTION ITEMS | COMMUNICATED TO | ASSIGNED TO | NO ACTION REQUIRED
Note on C9: Withrow, Cathy A: Left Message: LM Not Available: NA Call Back Requested: CB