## Sheet1
EAS PROJECTS MAPPED TO EP ACTION ITEMS - last updated 7/16/2009
Action # | Project Name | Project Description | Deliverables | Start Date | Target Date | Status | Manager | Related Action Items | Priority | Current Resources | $$ Needed | New Staffing Need
Action 7A -- Consolidated Infrastructure Services | [8 empty] | High
Action 7A -- Consolidated Infrastructure Services | EDS to ADS Migration for COMPASS |  |  |  | Aug 2009 | not started yet | Parmenter |  |  | part
Action 7C -- Consolidated Services | [8 empty] | High
Action 7C -- Consolidated Services | Constituent Relationship Management | Evaluate and select a single enterprise solution for CRM processing at IU. There are a few CRM products across the campuses and departments that will be consolidated. Additionally this solution will be rolled out to several more departments and campuses over the next couple of years. | 1) complete evaluation | 2009-05-01 | mid-April 2009 | completed | Chambers / Thompson | 52, 6 |  | 1 | yes | 1 base + 1 2yrappt
Action 7C -- Consolidated Services |  |  | 2) Negotiations and Purchase completed |  | July 2009 | in progress
Action 7C -- Consolidated Services |  |  | 3) Implement IUPUI Adms in enterprise solution |  | July 2009 | in progress
Action 7C -- Consolidated Services |  |  | 4) Establish Foundation & Alumni Strategy |  | Fall 2009 | in progress
Action 7C -- Consolidated Services |  |  | 5) develop rollout plan for current dept/campuses |  | Fall 2009 | not started
Action 7C -- Consolidated Services |  |  | 6) Establish Governance Committee |  | 2009-08-01 | not started
Action 7C -- Consolidated Services
Action 7C -- Consolidated Services | CC-28: Address Verification Software | Address verification software that can be used by Adms, Registrars, etc. This software can also be used by FMS, Payroll, Tax, and any other office that requires the use of accurate postal addresses |  |  | 1h, 2011 | start July 1 2010 with end date of June 30 2011 | Thompson |  |  | .25 fte | rfp for software
Action 7C -- Consolidated Services
Action 7C -- Consolidated Services | Online Admissions Application | 1) Development of a new enterprise system to process undergraduate Admissions applications. This system will replace two systems; the Apply Yourself vended application and the BL developed system. The retirement of the Apply Yourself system will eliminate a $7.00/application fee charged to each campus. |  |  | 2009-08-01 | in progress start Sept 2009 and end June 30 2011 | Thompson | 38 |  | 660 hrs (.30 fte)
Action 7C -- Consolidated Services |  | 2) AD-25: Professional School Application Upload |  |  | 1H, 2010 |  | Thompson |  |  | 1 fte /9 mo
Action 7C -- Consolidated Services |  | 3) AD-34: Graduate Online Application |  |  | Summer 2010 Spring 2010 |  | Thompson |  |  | 1 fte /9 mo
Action 7C -- Consolidated Services |  | 4) AD-28: Non-degree Online Application |  |  | 1H, 2010 |  | Thompson |  |  | 1 fte /6 mo
Action 7C -- Consolidated Services
Action 7C -- Consolidated Services | Develop & Deploy Scholarship application and processing system | Several campuses and departments were managing their own paper and/or web based scholarship applications. The COMPASS project offers an enterprise-level solution. | 1) Phase 1 - Automatic Scholarship Awarding |  | implemented Aug 2008 | completed | Parmenter | 38 |  | n/a
Action 7C -- Consolidated Services |  |  | 2) Phase 1b - Development of a dynamic self-service scholarship application used by the IU Foundation and IU South Bend |  | implemented February 2009 | completed |  |  |  | n/a
Action 7C -- Consolidated Services |  |  | 3) Phase 2 Development of student selective scholarship application and the ability for departments to make decisions and recommend students for specific awards |  | 2009-08-01 | in progress |  |  |  | 2 fte / 9 mo
Action 7C -- Consolidated Services |  |  | 4) Add FIS integration, listing of all IU scholarships and roll out to all remaining campuses |  | 2010-08-01 | pending approval |  |  |  | 1 fte / 6 mo
Action 7C -- Consolidated Services |  |  | 5) Phase 2b - IUPUI and Regionals |  | 2010-08-01 | not submitted yet |  |  |  | 2 fte / 6 mo
Action 7C -- Consolidated Services |  |  | 6) Phase 4 - All students including grads |  | 2011-08-01 | pending approval |  |  |  | 2 fte / 6 mo
Action 7C -- Consolidated Services
Action 7C -- Consolidated Services | Move School of Continuing Studies Course Management to Oncourse | SCS is currently using a departmental system known Dragon for their Course Management needs. They have decided to retire this system and migrate this process to the enterprise course management system. | 1) Begin using Oncourse for Online Semester Study Student course |  | Fall 2009 | in progress | Watkins | n/a
Action 7C -- Consolidated Services |  |  | 2) Implement WebEQ math editor |  | 2009-08-01 | in progress | Watkins |  |  |  | yes
Action 7C -- Consolidated Services |  |  | 3) Add all SCS people records to SIS |  | 2009-12-01 | in progress | Thompson start Sept 2009 and finish June 30, 2010 |  |  | .05 fte
Action 7C -- Consolidated Services |  |  | 4) Assign network ids to all SCS populations |  | 2009-12-01 | in progress | A. Walsh
Action 7C -- Consolidated Services |  |  | 5) Define a new SCS role in OneStart |  | 2009-12-01 | not started | Thompson
Action 7C -- Consolidated Services |  |  | 6) Build reports necessary for instructor payroll |  | Fall 2009 | not started | Watkins
Action 7C -- Consolidated Services |  |  | 7) Accommodate other SCS course work populations with Oncourse |  | Fall 2010/11 | not started | Watkins
Action 7C -- Consolidated Services | Oncourse consolidated infrastructure | Oncouse - move production database to Linux, consolidate all server resources at ICTC data center. |  |  | 2009 | not started | Watkins, along with EI managers
Action 7C -- Consolidated Services | Migrate Library Management System from AIX to Linux. (Library consolidated infrastructure.) | The SirsiDynix library system (staff functions and IUCAT) is available to run under a number of OS's. Currently under AIX, this project is to migrate it to Linux in line with UITS infrastructure strategic direction. | 1) setup of VMWare Linux virtual platform (ESA) |  | April 30, 2009 | Completed | McGreer
Action 7C -- Consolidated Services |  |  | 2) Install Sirsi Symphony 3.2.1 application software |  | May 1, 2009 | Completed
Action 7C -- Consolidated Services |  |  | 3) System and functional testing, including benchmark comparison with current AIX production version. |  | May 11-July 15, 2009 | Pending. Internal system testing in progress.
Action 7C -- Consolidated Services |  |  | 4) Production cut-over load testing. |  | July 15, 2009
Action 7C -- Consolidated Services |  |  | 5) Clone setup of parallel test system. |  | July 15, 2009
Action 7C -- Consolidated Services | dspace consolidation | related to action 55 and new enterprise wide office to manage Dspace, OpenJournal System, etc. |  | 2011-01-01 | July 2011 |  |  | 55 |  | 1 fte | hw | 1 fte
Action 16 -- Effective Partnerships (Community Source) | [8 empty] | Med
Action 16 -- Effective Partnerships (Community Source) | Community source involvement in development of a new Library Management system. | IU needs to participate actively in the Open Library Environment (OLE) project, an alliance of a multinational group of libraries developing the design for an open source alternative integrated library system. (http://oleproject.org/) | Participation in OLE to develop design document. | 2010-01-01 | Jan 2012 | IU is currently participating in regional meetings with 15 significant academic institutions. | IU Libraries Dean R. McDonald. (McGreer in collaboration with IU Libraries.) |  |  |  | 440000 | 2 2yrappts
|  |  | OLE implementation at IU | 2012-01-01 | Jan2013
Action 16 -- Effective Partnerships (Community Source) | Project Bamboo |  |  | 2013-01-01
Action 16 -- Effective Partnerships (Community Source) | Sakai - Partnership
Action 20 -- Business Continuity Program | [8 empty] | n/a
Action 20 -- Business Continuity Program | Laptops for all developers | Ensure that all EAS developers have laptop computers that are configured such that they can affectively work remotely if a disaster requires them to work away from the office (no reliance on remote desktop for example) | 1) All Oncourse & Library staff have adequate equipment |  |  | completed | Watkins & McGreer
Action 20 -- Business Continuity Program |  |  | 2) Purchase & configure laptops for 1st half of SIS team |  | April 2009 | completed | Parmenter
Action 20 -- Business Continuity Program |  |  | 3) Purchase & configure laptops for 2nd half of SIS team |  | 2009-08-01 | not started | Parmenter
Action 24 -- World Class IT Staff | [8 empty] | High
Action 24 -- World Class IT Staff |  | Develop proposal
Action 30 -- Reporting Tools | [8 empty] | High
Action 30 -- Reporting Tools | Develop a 'dashboard summary' application for Library management informatiion. | Develop a BI real-time dashboard summary of library statistics application for management and collection information. | application |  | 2010 | approved | McGreer
Action 31 -- Data Remodeling | [8 empty] | High
Action 31 -- Data Remodeling
| Archive & Purge Projects | Archive or purge large operational tables | 1) retire old SF records |  | unknown | not started yet | Parmenter
|  |  | 2) retire old FA records |  | unknown | not started | Parmenter
| Institutional Reporting Dimensional Tables | Develop multi dimensional tables to reflect the needs of the IR office | “IR Degree Completions” |  | Fall, 2009 | in progress | Parmenter
|  |  | "RG29 Summary Enrollment Report Replacement |  | Fall, 2009 | in progress | Parmenter
Action 34 -- Teaching & Learning Resources Data Utility | [8 empty] | Low
Action 34 -- Teaching & Learning Resources Data Utility | Opencast integration with Oncourse | Opencast integration with Oncourse - Developing an interface between Opencast and Oncourse will allow students and faculty in Oncourse to deploy and use Opencast materials |  |  | 2009 |  | Watkins
Action 35 -- CMS Integration with Open Educational Resources | done | [7 empty] | Med
Action 35 -- CMS Integration with Open Educational Resources | Open.iu.edu integration with Oncourse | Developing an interface between Onourse and Open.iu.edu will allow users of Open.iu.edu to access materials stored in Oncourse without having to authenticate | 1) Implement anonymous role and special permissions in stealth mode |  | Aug 2009 | in progress | Watkins | n/a
Action 35 -- CMS Integration with Open Educational Resources |  |  | 2) Implement anonymous role and special permissions unstealthed |  | Dec 2009 | not started | Watkins | n/a
Action 35 -- CMS Integration with Open Educational Resources
Action 35 -- CMS Integration with Open Educational Resources | Oncourse site export | Site Setup: Export file that can be saved to the desktop and then import course skeleton, facilitate sharing of course set-up and information |  |  | 2009 |  | Watkins | n/a
Action 35 -- CMS Integration with Open Educational Resources
Action 35 -- CMS Integration with Open Educational Resources | Integration: iTunesU with Sakai/Oncourse | Integration: iTunesU with Sakai/Oncourse |  |  | ongoing |  | Watkins | n/a
Action 35 -- CMS Integration with Open Educational Resources
Action 35 -- CMS Integration with Open Educational Resources | Podcast integration with Oncourse | Podcast: Add a note on the Add Podcast screen that states the file size limit, and what file types are supported by iTunes U. |  |  | 2009 |  | Watkins | n/a
Action 35 -- CMS Integration with Open Educational Resources
Action 35 -- CMS Integration with Open Educational Resources | Connexions Open Source | Collaborate with Connexions on integration with Sakai and/or implement as a new product at IU (Connexions is a place to share educational materials) |  |  | mid 2010 |  | Watson
Action 35 -- CMS Integration with Open Educational Resources
Action 35 -- CMS Integration with Open Educational Resources | Library system data integration available to OnCourse. | Feasibility study for making library data available for display in Oncourse via XML gateway, SQL, or call to Sirsi API tools. For use by Oncourse and other web apps to query data from Sirsi Symphony. For displaylibrary functions such as library notices, availability notices, etc. |  |  | 2009 | Not started. | McGreer |  | talk to David Goodrum
Action 38A - User Experience & Efficiencies | [8 empty] | High
Action 38A - User Experience & Efficiencies | (mostly usability)
Action 38A - User Experience & Efficiencies | Add a link to OneStart from Oncourse | We currently have the Oncourse Dashboard embedded in OneStart to make it easy for students to go from Student Self-Service to Oncourse. But we don't currently provide the same easy navigation from Oncourse to OneStart. So we will add a link to aid in this navigation. | add the link |  | 2009-08-01 | not started | Watkins | n/a
Action 38A - User Experience & Efficiencies
Action 38A - User Experience & Efficiencies | Change 4 tabs to 6 tabs in Oncourse | Based on student feedback, it was identified that students would like to have more than 4 course site tabs available across the top of the Oncourse application. This project will increase the number of tabs from 4 to 6. | implement Sakai 2.6 |  | June 2009 | in progress | Watkins | n/a
Action 38A - User Experience & Efficiencies
Action 38A - User Experience & Efficiencies | Change sort order of Oncourse tabs | Change the sort order on Oncourse tabs to show current semester courses first | new feature - Sakai 2.6 upgrade |  | June 2009 | in progress | Watkins | n/a
Action 38A - User Experience & Efficiencies
Action 38A - User Experience & Efficiencies | Oncourse Improvements | Collection of small projects to resolve issues and improve Oncourse |  |  | 2009 | not yet approved | Watkins | 38A
Action 38A - User Experience & Efficiencies
Action 38A - User Experience & Efficiencies | Turn It In/Oncouse integration | Turn it In Technical Evaluation( Integration of TurnitIn with Sakai/Oncourse assignment submission). |  |  | ? | ? | Watkins
Action 38A - User Experience & Efficiencies
Action 38A - User Experience & Efficiencies |  | Assignments 2 - continued gap development and contribute to Sakai |  |  |  |  | Watkins
Action 38A - User Experience & Efficiencies
Action 38A - User Experience & Efficiencies | Academic Advising Report (AAR) Usability Enhancements | Several delivered enhancements have been implemented for the Academic Advising Report (AAR). IU would like to apply some general improvements, usability, and features needed to benefit student usage of the audit. | make changes |  | 2009-12-01 | approved start now and complete by June 30, 2010 | Thompson | 45 |  | .25 fte
Action 38A - User Experience & Efficiencies |  | AA-27: AAR Multi-Instution coure list. Allow selection of inst on course list |  |  | 12/1/2009 or 1st half of 2010 |  | Thompson
Action 38A - User Experience & Efficiencies |  | AA-32: AAR grid sort. Change default grid sort to term by term oldest term first. |  |  | 12/1/2009 or 1st half of 2010 |  | Thompson
Action 38A - User Experience & Efficiencies |  | AA-29: Exceptions Display - directives and overrides: need both indicated on primary page in AAR |  |  | 12/1/2009 or 1st half of 2010 |  | Thompson
Action 38A - User Experience & Efficiencies |  | AA-30: AAR WHIF sort options: current displays options not available to students |  |  | 1st half of 2010
Action 38A - User Experience & Efficiencies | Planner Usability Enhancements (group with AAR Usability) | AA-36: Planner Course Roll. New column in planner grids to indicate Course Cat info change |  |  | 1st half of 2010 |  | Thompson
Action 38A - User Experience & Efficiencies |  | AA-37: Planner Term Note Stick: allow term notes to stick to grid even after courses removed |  |  | 1st half of 2010 |  | Thompson
Action 38A - User Experience & Efficiencies |  | AA-33: Planner Prereqs. Restore planner ability to display prereq info for planned courses |  |  | 12/9/2009 1st half of 2010
Action 38A - User Experience & Efficiencies
Action 38A - User Experience & Efficiencies | SPOSi - Self-Service Redesign | Redesign the Student Portal to provide for more integrated student services and a more student friendly environment. | 1) convene a group of customers to articulate needs and to help with initial designs |  | April 2009 | in progress | Chambers (McGough owns Action Item) | 45 |  | .25 fte - 2010 + .25 fte 2011
Action 38A - User Experience & Efficiencies |  |  | 2) Develop multi-year project plan |  | June 2009 | approved | Chambers | 45
Action 38A - User Experience & Efficiencies |  |  | 3) Phase 1 |  | Summer 2010 | approved | Thompson | 45
Action 38A - User Experience & Efficiencies |  |  | 4) Phase 2 |  | ? | approved | Thompson | 45
Action 38A - User Experience & Efficiencies | CC-30: Parent/Guardian Contact Self Service Page |  |  |  | May, 2010 |  | Thompson |  |  | est included in SPOSi
Action 38A - User Experience & Efficiencies | Student SS rewrite for FA |  |  |  | Aug 2011 |  | Parmenter | 45
Action 38A - User Experience & Efficiencies | Student SS rewrite for SF |  |  |  | Aug 2011 |  | Parmenter | 45
Action 38A - User Experience & Efficiencies | Library system notifications within SPOSI |  |  | 2010-01-01 | Summer 2010 |  | McGreer | 45
Action 38B - User Experience & Efficiencies | (mostly operational efficiencies) | [7 empty] | Low
Action 38B - User Experience & Efficiencies | (mostly operational efficiencies)
Action 38A - User Experience & Efficiencies
Action 38A - User Experience & Efficiencies | Automate MIL Communication Creation |  |  |  | Dec 2009 Feb 2010 | approved, not started yet | Parmenter |  |  | 655 + 480 for crs desc = 1135 hr = 55%
Action 38B - User Experience & Efficiencies | IU Course Approval & Remonstrance (CARMin) |  | 1) Undergraduate Course Approval and Remonstrance |  | Dec 2009 | in progress | Thompson | 7
Action 38B - User Experience & Efficiencies |  |  | 2) Convert Graduate Course Approval and Remonstrance from eDoc lite to heavy metal |  | Dec 2009 | in progress | Thompson | 7
Action 38B - User Experience & Efficiencies |  |  | 3) Updates Official Course Description in SIS |  | Dec 2009 (SWT says we need to move to Feb 2011) | in progress | Thompson | 7 & 45
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Automate Routing and Approval process for SF Item Types | In support of the need to streamline the budget and accounting associated with Scholarship processing for better tracking and compliance, we will develop an eDoc to support the creation and maintenance of SF item types. | Deliver eDoc |  | 2010-08-01 | approved but not started yet | Parmenter | 7
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Admissions Transmission Projects | High School XML Transcript Upload - The State of Indiana has selected Docufide as the vendor to provide XML High School transcripts. IU has signed with Docufide to be able to receive these XML files and automatically update the information into the SIS system. About 20% of high schools are currently participating. | automate the transmission and upload |  | 2009-08-01 | in progress | Thompson |  |  | .20 fte
Action 38B - User Experience & Efficiencies |  | AD-26: AP Test Scores Electronic Upload |  |  | 2009-12-01 |  | Thompson
Action 38B - User Experience & Efficiencies |  | AD-35: Receipt and upload of XML College Transcripts |  |  | 2h, 2010 1st half of 2011 |  | Thompson
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | AA-43: Advisor Assign - Office: allow units to assign an office to students instead of only individual advisors |  |  |  | 8/1/2009 1st half of 2010 |  | Thompson
Action 38B - User Experience & Efficiencies | AA-28: ability to permanently save an AAR: most units print and save a paper copy for accreditation |  |  |  | 12/1/2009 1st half of 2010 |  | Thompson
Action 38B - User Experience & Efficiencies | AA-45: Transfer Indiana Degree Audit integration |  |  |  | summer 2011 June 2010 |  | Thompson |  |  | 300 hr = .15 fte
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | CC-27: Ethnicity Changes for IPEDS reporting and data collection |  |  |  | 2009-12-01 |  | Thompson
Action 38B - User Experience & Efficiencies | SR-47: eTranscript Services - PDF Delivery of Transcripts to 3rd Parties |  |  |  | 1h, 2010 Dec 2009 |  | Thompson |  |  | 300 hr = .15 fte | rfp for software $15,000
Action 38B - User Experience & Efficiencies | CC-29: External System ID to display in Admin Center |  |  |  | 2009-12-01 |  | Thompson
Action 38B - User Experience & Efficiencies | Automate FA Budget Creation | Created a process on the batch schedule that would copy the Budget Run controls for an Institution and Aid Year to the delivered Budget Creation run control records to allow FA Budgets to be created in batch. Currently the FA Batch Budget Creation process only has one run control record that is keyed by process name, not USERID & Run Control name like most, therefore this process currently can only be run one at a time and run control values cannot be stored in advance to running the process. | automate creation |  | 2009-08-01 | in progress | Parmenter | n/a
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Modify Fee Remission System gateway to allow for revisions and Cancellations | Modify FRS Gateway to allow for revisions and cancellations to award entries even after entry has been linked to a Third Party Contract. Currently once the entry is linked to a TPC no adjustments can be done in the FRS Gateway. This causes users to make adjustments on SF TPC page which bypasses flow of data back to FA which can cause compliance issues with overawards. | Phase 1 |  | June 2009 | in progress | Parmenter
Action 38B - User Experience & Efficiencies |  |  | Phase 2 & 3 |  | 2009-12-01 | not started yet | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Dept. Schools awards in Offer when award disbursed |  |  |  | Dec 2009 | not started yet | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Modify GL interface to allow revenue to be split (SF-24) |  |  |  | Aug 2009 | not started yet | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Incoming Aggregate and Loan Year Level |  |  |  | Aug 2009 | in progress | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Correct Direct Loan Academic Year Start and End Dates |  |  |  | May 2009 | in progress | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Automate the Creation of Loan Entrance Checklists |  |  |  | May 2009 | in progress | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Automate Loan Exit Process |  |  |  | Dec 2009 | not started yet | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Modify Initial Edits Process to Complete Checklists |  |  |  | Dec 2009 Feb 2010 | not started yet | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Mid-Year Transfer Monitoring |  |  |  | Dec 2009 | not started yet | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | FA-43: Revise SSACI Estimate Program to estimate on correct ISIR Records |  |  |  | Feb 2010 | not submitted yet | Parmenter
Action 38B - User Experience & Efficiencies | FA-44: Modify Loaded Subsequent ISIR Process to be more selective |  |  |  | Feb 2010 | not submitted yet | Parmenter
Action 38B - User Experience & Efficiencies | QuikPay Credit Card Payments for Kelley |  | ? |  | Aug 2009 | in progress | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Interface with Barnes & Nobles |  | ? |  | Dec 2009 | not started yet | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Migrate issues tracking from Falcon to Footprints |  | ? |  | ? | in progress | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Modify GL RC Distribution |  | ? |  | Dec 2009 | not started yet | Parmenter
Action 38B - User Experience & Efficiencies
Action 38B - User Experience & Efficiencies | Ad Astra version 7.3 upgrade | The VII release of Ad Astra is a major re-engineering of the Room Scheduling software. | upgrade software |  | 2009-12-01 | not started | Thompson |  |  | 300 hr = .15 fte
Action 38B - User Experience & Efficiencies | eBuildScheduleof Classes |  |  |  | 1h, 2011 | *pending approval start in July 2010 and due by June 30, 2011 | Thompson |  |  | 500 hr = .25 fte
Action 40 -- Mobile Applications | [8 empty] | Med
Action 40 -- Mobile Applications | Proof of Concept with Boopsie | Working with Library and the mobility team to implement Boopsie as a smart phone infrastgructure to use for Library applications -- non sensitive datasets | test indexing. Extract subset of 250,000 records for Boopsie test |  | April 2009 | Completed. Testing in progress. | McGreer (McGough owns the infrastructure)
Action 40 -- Mobile Applications |  |  | move some sampling of applicatinos into production |  | 2009-12-01 | not started | McGreer
Action 40 -- Mobile Applications | Evaluate Duke iPhone app | determine if this functionality can be expanded to other devices |  | 2010-01-01 | 2010-07-01 |  | McGreer
Action 40 -- Mobile Applications
Action 40 -- Mobile Applications | Partnership arrangement with Blackberry and Oncourse | Work with Blackberry and moblity team to implement some set of Oncourse applications | define scope |  | May 2009 | in progress | Chambers (McGough owns the infrastructure) |  |  |  |  | 1 base for SIS & Oncr
Action 40 -- Mobile Applications |  |  | pilot some set of applications |  | 2009-12-01 | not started | Watkins
Action 40 -- Mobile Applications | boopsie functionality within an MIT framework |  | duplicate boopsie functionality | 2010-07-01 | Dec 2011 | approved | McGreer |  |  |  |  | 1 base for Lib team
Action 40 -- Mobile Applications | Student Self-Service Mobility |  |  |  |  | pending approval probably start in fy 11 (june 2010 thru June 2011) | Thompson |  |  | .25 fte
Action 45 -- Student Success & Improved Institutional Support | [8 empty] | High
Action 45 -- Student Success & Improved Institutional Support | Maintain Course / Class Descriptions |  | 1) Development of a maintenance transaction for class descriptions in the SIS and will including routing and approval |  | 2009-10-01 | not started yet | Thompson | 38B
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Integrate Course Descriptions into Schedule of Classes / Registration / Planner (CARMin Phase 3?) | Add the official and/or class descriptions into the registration process such that students can see this information prior to registering for a class. | Not sure if this will be added to schedule of classes search, the Academic Planner or search within registration or all |  | Oct 2009 | not started yet | Thompson | 38A |  | 180 hrs = .10 fte
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | SR-116: ITAP - Integrated Academic Planning | Phase 1 |  |  | 1h, 2011 Summer 2010 |  | Thompson | 38A |  | 1400 hrs (split over 2 yr) = .35 each yr
Action 45 -- Student Success & Improved Institutional Support |  | Phase 2 |  |  | 1h, 2012 |  | Thompson | 38A |  | see above
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | SR-84: Improving Student Waitlist | Phase 1 |  |  | Summer 2010 this will need to move to fy11 if we don't get a new SIS base position. Also may need to move due to timing of itap phase 2 |  | Thompson |  |  | 300 hr = .15 fte
Action 45 -- Student Success & Improved Institutional Support |  | Phase 2 |  |  | 2h, 2010 |  | Thompson
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | SR-999: Program / Plan Updates |  |  |  | 2011 planning to start in Jan 2011 and due by June 2011 | *pending approval | Thompson | 38B |  | 500 hrs = .25
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | SR-999: Apply for Graduation |  |  |  | Feb 2010 1H, 2011 | *pending approval | Thompson | 38B |  | 500 hrs = .25
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | WR-507: eSpecial Credit (eDoc lite --> Heavy Metal) |  |  |  | 2h, 2010 | *pending approval | Thompson | 38B |  | 300 hrs = .15 fte
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | SR-999 Administrative Registrations - Continuing Students |  |  |  | 1h, 2011 | pending scope | Thompson |  |  | 100 hrs = .05 fte
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Complete Title IV Waiver via SS |  |  |  | Aug 2009 | in progress | Parmenter
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | IRS Form 1098-T Self-Service |  |  |  | Dec 2009 if missed Dec 2010 | not started yet | Parmenter
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Financial Aid Steps in Student Self-Services |  |  |  | 2h 2010 | approved | Parmenter
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Extend Drop/Add period by one week for IUBLA students |  |  |  | Dec 2009 Feb 2010 | approved | Parmenter
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Early Warning System | Develop an application that allows faculty to report issues with student's progress early enough in the semester to give advisors an opportunity to determine what the underlying problems might be. | 1) IUPUI needs to more efficiently administer their Early Warning policy whereby all University College students are given timely feedback on class performance. We will leverage the SIS Mid-term roster for this purpose short-term. This will be linked into Oncourse for easy faculty access. |  | Dec 2009 | in progress | Thompson | see Action #68
Action 45 -- Student Success & Improved Institutional Support |  |  | 2) Long-term solution . . . |  | ? | not approved | Watkins | 38A
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Turn on Advanced Search capability in Class Search | Improve student’s capability to search for classes that better match their needs by turning on advanced search functionality in PeopleSoft. This functionality was available but was not turned on by default. Also, make a few usability changes to make this feature more usable. | turn it on and make usability changes |  | April 2009 | completed | Thompson | 38A
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Turn on Synoptic Tool for Oncourse Messages | This is a very useful tool that was turned off last August due to performance issues. Students have requested that this functionality be turned back on so they have a summary view of all of their course messages in one place without having to go into each individual course site. | make tuning changes and turn it on |  | June 2009 | in progress | Watkins | 38A
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Inplement "Grad Tools in Oncourse | Implement "Grad Tools" checklist manager in Oncourse. This tool was designed by uMich to manage requirements and processes defined by the graduate school and department. The code should be in a sharable state sometime after July. |  |  | not yet known | not yet approved | Watkins | 38A
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Oncourse OCS integration | Assess feasibity of integrating Oncourse with Office Communications Server (OCS) to facilitate communication and collaboration amoung students and faculty. |  |  |  |  | Watkins
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Integrate Oncourse Syllabus into Registration | Provide Syllabus information as part of the Schedule of Classes, Registration process and/or Student Planner process to allow the student to have as much information about a course as possible prior to registration. | this may take some changes in faculty business practice since some syllabus information is not available until after registration. |  | not yet known | not yet approved | Watkins / Thompson | 38A
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Academic Advising Report, Planner and Enrollment Integration | There are many PS delivered enhancements that we are turning on and/or modifying to provide better integration between the Student Planner, Academic Advising Report, Registration and Shopping Cart. These are being implemented as quickly as possible as part of this initiative. | 1) In March 2008 the Student Planner was released via the Student Center. The Planner is an online tool for students to list and organize courses that they may want to take at IU. This is accomplished by selecting courses from the IU Course Catalog. The Planner is integrated with the enrollment process via the Shopping Cart, providing students with an alternative to using the 'Class Search' function when selecting classes for enrollment. |  | Announced last year | completed | Thompson | 38A
Action 45 -- Student Success & Improved Institutional Support |  |  | 2) New Integrated Degree Audit (AAR) and Integrated with Student Planner - new web-style AAR, integrated via links to other information in SIS and integrated with Planner. In addition to using the Course Catalog, students will be able to use the AAR to select courses to be added to the Planner, and the Planner will display what requirement the course will meet. Thus, the AAR will have a transitive integration with enrollment as of this release. |  | May 2009 | completed | Thompson | 38A
Action 45 -- Student Success & Improved Institutional Support |  |  | 3) Register by Requirements - Use Shopping Cart and search for courses for enrollment in 3 ways: using the Class Search, the Planner, or the Advisement Report. Students can SIS to see degree requirements, see which ones are not completed and which classes will meet them, and enroll in classes in the same online process. |  | 2009-12-01 | not started | Thompson | 38A
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Deploy Clearinghouse link from Student Self-Service in OneStart | IUB has partnered with the National Student Clearinghouse to provide enrollment and degree verifications for students. This service allows students to use NSC’s online services for verifying enrollment, degree information or certifying their good student discount for insurance companies. This project will allow students to now go through CAS authentication to access these Clearinghouse services from OneStart. | implement link |  | Aug 2009 | in progress | Thompson | 38A
Action 45 -- Student Success & Improved Institutional Support
Action 45 -- Student Success & Improved Institutional Support | Library Federated Searches | integration with Oncourse |  | 2010-01-01 | Summer 2010 |  | McGreer | 38A
Action 46A -- Student Activities & Calendaring | [8 empty] | Med
Action 46A -- Student Activities & Calendaring | Enterprise Solution for Student Activities | The BL Student Affairs office along with several other BL departments are interested in acquiring a software product that will allow clubs to communicate with members. Additionally, students want to keep track of their extra-curricular activities in one place (those related to IU and those outside of IU). IUPUI already has a product like this so we will be looking to consolidate this service as part of this action item. | 1) acquire the StudentLink product from CollegiateLink as a short-term solution |  | July 2009 | approved | Chambers | 7, 45 |  | yes | yes | 1 IPS + 1 SIS (adding ips because of CRM, Ad Astra, AddressV, SA-Link)
Action 46A -- Student Activities & Calendaring |  |  | 2) Implement StudentLink in enterprise environment |  | 2009-08-01 | approved | Parmenter | 7, 45
Action 46A -- Student Activities & Calendaring |  |  | 3) do a software evaluation to determine if an enterprise license of StudentLink is what IU needs or if we should develop an in-house solution. Decision by Aug 2010 |  | 2010-08-01 | approved | Parmenter | 7,45
Action 46A -- Student Activities & Calendaring |  |  | 4) Implement product or develop/implement a custom application |  | 2011-08-01 | approved | Parmenter | 7, 45
Action 46A -- Student Activities & Calendaring |  |  | 5) consolidate IUB and IUPUI onto one system |  | Aug 2011 | pending approval | Parmenter | 7,45
Action 46A -- Student Activities & Calendaring
Action 46A -- Student Activities & Calendaring | Interface with Barnes & Nobles in order to post charges into SF |  |  |  | 2009-12-01 | not started | Parmenter
Action 46A -- Student Activities & Calendaring
Action 46A -- Student Activities & Calendaring | QuikPay Credit Card Payments for BL Kelley Direct |  |  |  | 2009-08-01 | not started | Parmenter
Action 46B -- Student Activities & Calendaring | [8 empty] | Med
Action 46B -- Student Activities & Calendaring | Integrate Class Schedule with OneStart Calendar | Feed student class schedule calendar information to the enterprise calendar | do programming and work with OneStart time for integration |  | not yet known for planning we'll go with 1st half of 2011 (fy10-11) | not approved | Thompson | 38A, 45 |  | 300 hrs = .15 fte
Action 46B -- Student Activities & Calendaring | Integrate Student Activities Calendar with OneStart calendar | Feed SAO club and organization calendars to the enterprise calendar | do programming and work with OneStart time for integration |  | 2011-08-01 | not approved | Parmenter | 45
Action 46B -- Student Activities & Calendaring | Need something here for Oncourse |  |  |  | ? | ? | Watkins | 45
Action 48 -- Learning Administration (Flexible Learning Units) | [8 empty] | Low
Action 48 -- Learning Administration (Flexible Learning Units) | Add New Graduate Career for Kelley Direct | Add a new grad career in PeopleSoft to support accellerated programs. To date, administrators in the Kelley Direct program along with the Office of the Registrar/Student Financial Services/Financial Aid offices manage a number of synchronization issues between the Kelley Direct accelerated program calendar and the traditional SIS GRAD calendar. The issues and complications begin during the admissions application process and continue through matriculation, enrollment, fee assessment, financial aid packaging and disbursement. | Add new career |  | May 31, 2009 | completed | Parmenter | 45
Action 55 -- Recapture Scholarly Works (Supporting) | [8 empty] | Low
Action 55 -- Recapture Scholarly Works | Establish an enterprise-wide office to support Scholarlyworks and dspace activity | ES Supporting |  |  |  | retreat in July | Chambers / Watkins | 7C
Action 57 -- eTextbooks | [8 empty] | Low
Action 57 - eTextbooks | Katana/McGraw Hill integration with Oncourse | This integration allows faculty in Oncourse to direct students to McGraw Hill materials |  |  | completed | completed | Watkins | n/a
Action 66 -- Digital Materials | [8 empty] | Low
Action 66 -- Digital Materials | SCORM | integrate SCORM standards into Sakai 2.7 |  |  | June 2010 |  | Watkins
Action 66 -- Digital Materials |  | Evaluate use of rSmart's integration ICONDIAN SCORM READER into Resources (requires licensing fees for ICONDIAN) | evaluate in fall 2009 pilot in Spr 20010 prod in Fall 2010 |  | Fall 2010
Action 66 -- Digital Materials |  | SCORM integration with Gradebook
Action 66 -- Digital Materials |  | SoftChalk building SCORM templates -- IU should consider becoming a BETA user
Action 66 -- Digital Materials |  | Integration of Raptivity (creates SCORM objects)
Action 67 -- Distance Education | [8 empty] | Med
Action 67 -- Distance Education | Sakai3 | includes social networking |  |  | 2011 | in progress | Watkins
Action 67 -- Distance Education | Integration with Adobe Connect | (look at rSmart's Illuminate's integration) |  |  |  |  | Watkins
Action 67 -- Distance Education | Google Doc integration with Oncourse | Google Doc integration - work with Sakai community to integrate Google applications such as Google Docs and perhaps other components into Sakai |  |  | Dec 20009 |  | Watkins | n/a
Action 67 -- Distance Education |  | Google Wave integration in Sakai 3 |  |  | 2011 |  | Watkins | 66
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | [8 empty] | High
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | ePortfolio | ePortfolio - continuing development and support (see confluence template for details) | TBD |  | ongoing | ongoing | Watkins
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) |  | Move into Sakai3 | TBD |  |  |  | Watkins
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative)
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | Early Warning System | Develop an application that allows faculty to report issues with student's progress early enough in the semester to give advisors an opportunity to determine what the underlying problems might be. | 1) IUPUI needs to more efficiently administer their Early Warning policy whereby all University College students are given timely feedback on class performance. We will leverage the SIS Mid-term roster for this purpose short-term. This will be linked into Oncourse for easy faculty access. |  | May 2009 | in progress | Thompson | see Action #45
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) |  | the Learning Technologies and the Oncourse Development Team will scope out and develop a more flexible and robust system within Oncourse that provides students, faculty, advisors, and administrators with information and feedback on student performance as well as tools for facilitating interventions when necessary. |  |  | June 2010 |  | Watkins
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) |  | IUPUI Card Services Swipe for Attendance |  |  | Aug 2009 | in progress | Watson
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative)
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | Oncourse Test/Survey Tool retirement | Retire Test and Survey Tool in Oncourse Original. Implement Sakai compatible replacement tool such as Samigo or Mneme. This project will also include tasks related to the retiement of OC Original and will require data conversion and data load stratgies to be devised. |  |  | Dec 2010 | approved | Watkins
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative)
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | Redesign Site Stats | improve underlying data structure and improve the user interface | there is a new contrib tool that doesn't seem to meet IU's need |  | June 2010 | approved | Watkins
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative)
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | Oncoure/iRubric integration | Integrate iRubric (rubric scoring tool) into Sakai/Oncourse. Initial deployment for IUB School of Education. Use by other campuses and schools TBD. | Implement SOE pilot project to demonstrate integration with gradebook and Assignments 2 in Oncourse |  | summer / fall 2009 | approved for intial research and pilot | Watkins
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative)
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | Oncourse/PUL collection | Oncourse tool for data collection of faculty ratings of students' mastery of IUPUI Principles of Undergraduate Learning (PUL). Reporting of results via IUIE |  |  | Oct 2009 |  | Watkins/ Thompson | should be an sis project
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative)
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | Establish an Assessment Strategy for Schools | Project to define requirements for tools for data collection, aggregation and reporting to support accreditation and assessment activities by schools and departments |  |  | 2010 |  | Watkins
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative) | Online Course Evaluations |  |  |  | Oct 2009 |  | Watkins
Action 68 -- Assessment and Feedback Systems (key Oncourse initiative)
Action 69 -- Mobility for Teaching and Learning | [8 empty] | Med
Action 69 -- Mobility for Teaching and Learning | Integration: Clicker device with Sakai/Oncourse | Implement integration with clicker with Oncourse. Will include registration of clickers by students within Oncourse and integration with gradebook to record scores from clicker. Need specs once vendor is selected and Sakai integration is defined |  |  | Aug 2009 |  | Watkins | n/a
Action 69 -- Mobility for Teaching and Learning | Integration: ResponseWare | Turning Point's ResponseWare software provides a BB and iPhone version to allow students to use their mobile device instead of the clicker |  |  | Aug 2009 |  | Watkins | 40
Action 69 -- Mobility for Teaching and Learning | Sakai Mobile Portal | Improve sakai tools so they work effectively within IU mobile gateway framework |  |  | various |  | Watkins | 40
Action 69 -- Mobility for Teaching and Learning |  | Make Assignments 2 mobile ready |  |  | Dec 2009 |  | Watkins | 40
Action 69 -- Mobility for Teaching and Learning |  | Make Discussion, Gradebook, Announcements mobile ready |  |  | June 2010 |  | Watkins | 40
No Action - Required Maintenance and Support | [8 empty] | Med
No Action - Required Maintenance and Support | Archive Purge for SF |  |  |  | Aug 2010 | in progress | Parmenter
No Action - Required Maintenance and Support | Archive Purge for FA |  |  |  | Aug 2010 | in progress | Parmenter
No Action - Required Maintenance and Support | PS SIS PUF/Releases |  |  |  | various | various | Thompson/Parmenter
No Action - Required Maintenance and Support | PS Tools Upgrade |  |  |  | various | various | Thompson/Parmenter
No Action - Required Maintenance and Support | HR/SIS Split and Data Hub implementation |  |  |  | 2012 |  | Thompson/Parmenter
No Action - Required Maintenance and Support | Remini Street |  |  |  | 2011 |  | Thompson/Parmenter
No Action - Required Maintenance and Support | Oracle 11 upgrade |  |  |  | Jun 2011 |  | Thompson/Parmenter/McGreet/Watson
| Data Center Move |  |  |  | 2010 |  | Parmenter
| GL Support |  |  |  | various |  | Parmenter
No Action - Required Maintenance and Support | Oracle 12 upgrade |  |  |  | Jun 2011 |  | Thompson/Parmenter/McGreet/Watson
Action 27 -- Human Centered Support | [8 empty] | Med
Action 27 -- Human Centered Support |  | ES Supporting
Action 32 -- Records Mgmt | [8 empty] | Low
Action 32 -- Records Mgmt |  | ES Supporting
Action 39 -- Accessibility | [8 empty] | Low
Action 39 -- Accessibility |  | ES Supporting
Action 41 -- Federated Identity | [8 empty] | Low
Action 41 -- Federated Identity |  | ES Supporting
Action 42 -- Authorization Systems | [8 empty] | Low
Action 42 -- Authorization Systems |  | ES Supporting
Action 51 -- IT Transfer (Supporting) | [8 empty] | Low
Action 51 -- IT Transfer |  | ES Supporting
Action 52 -- Alumni Outreach (Supporting) | [8 empty] | Low
Action 52 -- Alumni Outreach |  | ES Supporting
Action 57 - eText Books (Supporting) | [8 empty] | Low
Action 57 - eText Books |  | ES Supporting
Action 61 -- Health Care Data Access (Supporting) | [8 empty] | Low
Action 61 -- Health Care Data Access |  | ES Supporting
Action 62 -- Health Care Shared Resources
Action 62 -- Health Care Shared Resources |  | ES Supporting
Action 64 -- T&L Learning Spaces | [8 empty] | Low
Action 64 -- T&L Learning Spaces |  | ES Supporting
Action 65 | [8 empty] | Low
Action 65 |  | ES Supporting
Action #70 -- IT Enabled Research (Supporting) | [8 empty] | Low
Action #70 -- IT Enabled Research (Supporting) |  | ES Suppporting
Action #71 -- IT Enabled Resourch Resources (Supporting) | [8 empty] | High
Action #71 -- IT Enabled Resourch Resources (Supporting) |  | ES Supporting